## Slide 1: TDR discussion
Jérôme Baudot
Reminder from last discussion
Discussion on writing organisation
    identify main writers for VTX sections
    agree on first milestones
2nd General VTX workshop
20-22 April 2026, DESY https://indico.belle2.org/event/18167

## Slide 2: Outcome from last workshop discussion
  Belle II upgrades form a single TDR document
    VTX is a chapter within this document
  Writing of the VTX sections could start already mid-2026 (after VTX workshop)
    completion expected mid-2027
  January 2027: main results from demonstrators & design drawings complete
  Expect in-coming results till the end of the writing
  Table of Contents (preliminary level)
    Overall concept
    Detailed concept
    Construction and installation
    Project structure (management, organisation, responsibilities, structure of work-packages, schedule, milestones, decision making, contingency)
    Resources (budget, person-power, risk, descoping option?)

## Slide 3: Current list of technology demonstrators
  Extracted from: https://vtxupgrade.pages.desy.de/vtxdvpmt/tdr/tdr-demonstrators/
  OBELIX-1 characterisation
  Demonstration that quality-assurance of OBELIX-1 can be conducted with a probe-station.
  RDL
  Thermic mock-up of 1 ladder
  Thermic mock-up of a 2-layer sector.
  Complete iVTX drawing
  Dummy L6 ladder
  Dummy oVTX sector
  Flex
  Complete oVTX drawing
  Complete VTX drawing
  Basic read-out chain wo final back-end

## Slide 4: Identifying “Main writers”
  Overall concept
    Performance specific to VTX ?
    General description
  Detailed concepts
    Sensor
    iVTX ladder
    oVTX ladder
    DAQ, control
    Trigger
    Monitoring
    Mechanical structure
  Construction and installation
  Project structure (see previous slide)
  Resources (budget, person-power, risk)
  Proposal:
    Vidya
    Jerome
    Hung
    Adrian, Emi
    Stefano
    Christian
    ?
    ?
    ?
  too early
  Jerome, …
  Jerome, Adrian
  Missing (sub-)section on data reconstruction,alignment?

## Slide 5: TDR schedule
  TODAY: kick-start of “writing”
  Next VTX workshop end of 2026: large fractions already written
  BPAC ~Feb. 2027: Main results from demonstrators & design drawings complete
  Jan-April 2027: writing completion
  May-Jun 2027: internal VTX commenting / amending
  Mid-2027: TDR document ready for Belle II internal review
Continuous integration of new results

## Slide 6: First milestones
  Overall concept
    Performance specific to VTX ?
    General description
  Detailed concepts
    Sensor
    iVTX ladder
    oVTX ladder
    DAQ, control
    Trigger
    Monitoring
    Mechanical structure
  Construction and installation
  Project structure (see previous slide)
  Resources (budget, person-power, risk)
Proposal:
  B2GM July 2026: detailed ToC for sections 1, 2
  B2GM Oct. 2026: detailed ToC for sections 3, 4, 5
  End of 2026: sections 1, 2 mostly written
    missing parts OK (e.g. OBELIX-1 results, …)
  March 2027: sections 3, 4, 5 mostly written